## Slide 1
SOLID: View from Hall A
Robert Michaels, Acting Hall A Leader
Issues to Discuss
Schedule of Experiments
Procedures to Decide Schedules
Budget and Manpower Estimates

## Slide 2
12 GeV Experiments
Days Major New Equipment
(e.g. tritium target or SBS)
GMp (elastic FF at high Q2) 24 none
(Moffit et.al.)
A1n (neutron spin structure) 23 none
(Bogdan W., et.al.)
DVCS (GPDs) 100 none
(Hyde et.al.)
APEX (dark matter) 34 none
(Bogdan W., et.al.)
GMn, GEn (high Q2 FF) 75 SBS
(Bogdan W., et.al.)
GEp (high Q2 FF) 45 recoil polarimeter
(Bogdan W., et.al.) in SBS
(some still unrated by PAC)
Continued ….
Possible early running

## Slide 3
12 GeV Experiments
Days Major New Equipment
(e.g. tritium target or SBS)
SIDIS w/ SBS conditional SBS
(Bogdan W., et.al.)
F2n/F2p (d/u from He3/H3) 42 tritium target
(Petratos, et.al.)
Moller (precision electroweak) 344 Moller spectrometer
(K. Kumar, et.al.)
SIDIS w/ SOLID 90 SOLID spectrometer
(H. Gao, et.al.)
PVDIS w/SOLID 169 SOLID spectrometer
(P.A. Souder)
(continued)
Continued ….

## Slide 4
Possible Other Experiments
Major New Equipment
Hypernuclear Physics TBD HKS, new septum magnets
(Tang, et.al.)
PREX-II 25 none
(Paschke, et.al.)
SRC ?
Other new ? TBD

## Slide 5
“Strawman” Flow-Chart for Schedule
Hall A is the first to take beam in 12 GeV Era !!
Commissioning Phase
(Hall A = beam dump for tests and engineering runs. No physics promised, but may be possible ?)
Mid- 2013 - Fall 2014
Early Experiments ?
Fall - 2014 - Fall 2015
Build SBS ,
Stage Moller and SOLID Apparatus
Early 12 GeV Experiments
(research-quality beam in FY15)
Meanwhile …
~2016
SBS Experiments
Continue to Stage Moller and SOLID
~2017+
Moller & SOLID Experiments
(interleaved with other experiments , e.g. SBS. need removable apparatus)

## Slide 6
How to Decide
Plan for Commissioning
Plan for Early Experiments
Schedule for SBS
Schedule for Moller and SOLID
Interleaving of Experiments
Depends on
Availability of Commissioning and Research Beam
Funding Realities
Scheduling Constraints of other halls.
Input from Users
Scientific Leadership of Lab
DOE deliverable: FY15

## Slide 7: Input from Users
Hall A Coordinating Committee to Select a Planning Committee.
Suggested membership: spokespersons of approved experiments.
E-mail and phone meetings prior to HA Collab. Mtg. (twice per year).
Chairman to report findings at HA Mtg.
Recommend priorities for sequence of commissioning and early experiments.
Recommend priorities for sequence and interleaving of large-project era experiments (SBS, Moller, SOLID).

## Slide 8: Manpower and Budget Exercises
Hall A manpower
Adding an electrical engineer (power supplies)
Made a young designer permanent (C. Soova)
Working on adding tech(s).
# of Scientist Staff to remain constant (rel. to FY2004)
Hall A budget ( ~ supplemental)
4.5 M$ for SBS MIE (submitted)
1 M$ for tritium target
21 M$ for Moller (not submitted yet)
??? for SOLID
for Rolf, aiming towards FY18
completed
In progress