## Slide 1: DOE Visit
Nov. 24, 2015

## Slide 2: Attendees
DOE
  Tim Hallman
  Gulshan Rai
  Jehanne Gillo
  A number of others
JLab: Rolf
SoLID
  Paul, Haiyan, JP, Zein-Eddine

## Slide 3: Presentations
Overview of SoLID (Haiyen)
Pre R&D Plan for SoLID (Paul)

## Slide 4: Content of the Meeting
SoLID is well supported by the LRP
Project has not been approved yet
DOE plans to move forward
Work out a time line with JLab management:
  First draft of MIE (Spring 2017)
  DOE Science Review is the next step (Summer 17)
  JLab (Rolf) will certify readiness
DOE requires one contact person (Paul)
SoLID can request Pre R&D funds, asked to provide a plan

## Slide 5: (Pre-)R&D Plan
1. Late 2016: Address first set of recommendations from the Director’s Review in order to prepare for the DOE Science Review.
2. Spring 2017: First draft of MIE
3. Summer 2017: DOE Science Review
4. 2020: Project Start
We are requesting support from the DOE so that we can meet this schedule.
Schedule

## Slide 6
2. Plan to address the Recommendations in the Director’s Review
Following is our plan to address the recommendations given in the Director’s Review: The numbers are the order of the recommendations in the report of the Director’s review.
1. Completed: 15 (MRPC glass stability).
2. To be completed before DOE Science Review:
2. Simulation of performance for core measurements
3. Development of a plan for the precision calibration of Q2 for PVDIS
4. Bin migration for J/Psi
5. S/B trigger rates for J/Psi
6. DAQ deadtime
8. SIDIS comparisons with SBS and CLAS12
26. Baffle optimization
1/7/16/24 (full simulation/software frame), significant parts will be done, (full version will be a long-term effort)

## Slide 7
2 Plan to address the Recommendations in the Director’s Review (cont.)
3. To be complete before MIE: (in addition to above) 11. R&D plan with timeline
23
12/13. GEM foils, assist Chinese group and schedule risk/backup plan
14. ECal, contact other groups. This process has started and will continue as we progress.
21. Plan for trigger/slow control
22. Resource needs
23. Communication
25. Calculation of radiative corrections
Project management :(27, 28, 29, 30, 32, 34, 35, 36)
Other items related to the magnet: (18, 19, 20, 31,33) will either be done, or have a plan to be addressed.
4. The following items are being worked on, but the full solution will be a long-term effort:
1/7/16/24 full simulation/software framework
9/17. Kaon identification: looked into options, improvement in MRPC-TOF most promising
10. develop GPD program: TCS approved; DDVCS, LOI submit- ted, proposal under development
Transverse polarized DVCS under development Full GPD program will require funding beyond base line (Muon detection, ...)

## Slide 8
3.5 Present DOE-sponsored University Effort
1. Duke: 1.65 FTE (Tracking, Software, SIDIS Systematics, and HGC)
2. Syracuse: 1.5 FTE (PVDIS Systematics)
3. Stony Brook: 0.75 (Software framework)
4. UVA: (Xiachao Zheng) ECal:, SPD’s 0.5 FTE (Testing prototypes)
5. UVA: (Nilanga Liyanage) GEM’s: 0.25 FTE (Developing large area GEM’s, coordinate with Chinese)
6. Temple: 0.2 FTE (J/Ψ systematics, LGC)

## Slide 9: SoLID Organization

## Slide 10
3.1 Goals for the first year
During the first year, we will address the following key issues:
1. Simulations/Reconstruction (11 recommendations)
2. Magnet and integration (5)
3. DAQ/Electronics (4)
3.2 Goals for the second year
4. Electron PID/Trigger (ECal, Ligh Gas Cherenkov) (3)
5. Hadron PID (TOF-MRPC and Heavy Gas Cherenkovs) (3)
6. Tracking/GEM (2)

## Slide 11
3.3 Request for the first year (2016) from the DOE
1. Simulations/Software: 3 postdocs total
(a) 1.5 for Stony Brook work with Seamus Riordan/Abhay Desh- pande/Tom Hemmick,
(b) 1 for Duke, work with Zhiwen Zhao/Haiyan Gao (c) 0.5 for Temple, work with Zein-Eddine Meziani.
2. Magnet
(a)Magnet transportation and performance testing: JLab
(b) 3-d modeling and integration: 0.8 FTE (Argonne)
3. DAQ: (JLab resource excluded) $73 K equipment 0.5 postdoc (Stony Brook, work with Krishna Kumar/Abhay Despande).
.
Total: First year: $73 K and 4.3 FTE (mainly postdocs).

## Slide 12
3.4 Requests for the second year (2017)
4. Electron PID: $107K, 1.6 FTE
(a) ECal (including SPD): (Chinese contributions excluded): $20 K equipment and visitor support, 1.1 FTE (UVa, work with Xiaochao Zheng)
(b)Light Gas Cerenkov: $87 K equipment, 0.5 FTE (Temple, work with Zein- Eddine Meziani)
5. Hadron PID: $212 K equipment, 1.2 FTE
(a)Heavy Gas Cerenkov: (Canadian contributions excluded) $121K equipment, 0.8 FTE (Duke, work with Haiyan Gao)
(b) MRPC: $91K, 0.4 FTE (Chinese contributions excluded) (Institution TBD)
6. GEMs: (Chinese contributions excluded) $80 K procurement and visitor support (UVa, Nilanga Liyanage and Temple, Bernd Surrow)
Total: Second year: $399 K and 2.8 FTE (mainly postdocs).